## Sheet1
Issue | Priority | Projected Completion Date | Completed?
In the front Sales grid, include the short SWIS code (i.e. last 2 digits) on the print key. | High | 2013-11-25
Remove the ranking number from the front Sales grid. | Med | 2013-11-25
Add the Building Style Description to the filter selection list. | Med | 2013-11-25
Add the Adjusted Market Value to the front Sales grid. | High | 2013-11-25
On the Appraisal Results Sheet:
- The total adjustment is not showing. | High | 2013-11-25
- Building style description should display. | High | 2013-11-25
- Swis code needs to display on print key. | High | 2013-11-25
- Basement description should display. | High | 2013-11-25
- School code should display. | High | 2013-11-25
Other adjustments:
- Air conditioning: $4,000. | High | 2013-11-25
- Inground pool (LS1, LS2, LS3): $10,000. | High | 2013-11-25
- Finshed rec room | High | 2013-11-25
Add in-place editing for pictures (in order to remove watermarks). | Med | 2013-12-02
If a sale is added which is not in range, the application crashes. | Med | 2013-12-02