## Sheet1
Issue | Priority | Projected Completion Date
In the front Sales grid, include the short SWIS code (i.e. last 2 digits) on the print key. | High | 2013-11-25
Remove the ranking number from the front Sales grid. | Med | 2013-11-25
Add the Building Style Description to the filter selection list. | Med | 2013-11-25
Add the Adjusted Market Value to the front Sales grid. | High | 2013-11-25
Grade/Condition drop-down filter, etc., has #, but needs words | High
Take out "First Floor Area", but leave in "Square Foot Area" (as this is total of 1st & 2nd Floors) | High
Entire page does not display on screen as it is too long horizontally | High
Subject is not showing Acreage….the word is there, but it is not being picked up from PAS | High
Time Adjustment being done on some comps, but not others | High
Is Timing Adjustment something we can edit? | High
Half Baths are not being picked up | High
Garages are being picked up incorrectly…Defender needs to read ResBldg page and ADD all 3 garage types together | High
Add 411C in Propety Class filter | High
Add "Zoning" on Comps (being picked up on Subject) | Med
In the "Ranges" drop down filter, we need to be able to choose more than one range for square footage | High
On the Map, please take out the address (only blank grey box prints); instead have Comp # print INSIDE the balloon | High
Can the Subject balloon maker be red and each comp be blue (or any color different from subject)? | High
Each time we run an appraisal, close and try the SAME one again, we get different picture results | High
Is it possible to dbl click on a picture and have Defender go directly to the PAS Pictures page of the individual property | High
and show ALL the choices for that property for us to pick the one we want for EACH Comp and for the Subject?
We need the ability to Edit pictures and SAVE them so they override what was originally there | High
If we EDIT a picture (crop out date, etc) we need for it to be SAVED so that when we choose that comp again, it will not need to be edited again | High
Arrange comps on the Appraisal by Final Adjustment Highest to Lowest | High
“Year Built” should move to the adjustments section at bottom and have an adjustment of $500/year | High
If we “save” the appraisal, it saves as a “.grd” and we don’t know how to open this | High
On the Appraisal Results Sheet:
- The total adjustment is not showing. | High | 2013-11-25
- Building style description should display. | High | 2013-11-25
- Swis code needs to display on print key. | High | 2013-11-25
- Basement description should display. | High | 2013-11-25
- School code should display. | High | 2013-11-25
- Add to top, right under Sale Date, "Lead Days" and show # days form date of sale to valuation date | High
- Pick up Half Bath adjustment ($2,500) | High
Other adjustments:
- Air conditioning: $4,000. | High | 2013-11-25
- Inground pool (LS1, LS2, LS3): $10,000. | High | 2013-11-25
- Finshed rec room ($20/sf) | High | 2013-11-25
Add in-place editing for pictures (in order to remove watermarks). | Med | 2013-12-02
If a sale is added which is not in range, the application crashes. | Med | 2013-12-02
We appreciate your efforts in delivering us with defender.
As some of these major components are not yet working, we may have further adjustments to make once these things are up and running. Thanks
This e-mail is the most recent and last until you can review and make some changes.
Mike , every day that arent working with Defender we cannot proceed with our 2013 SCAR complaints and we are receiving calls from homeowners.